## Sheet1
UI | Create a new function In game.js to remove a player from the view and puts the waiting circle back
UI | All in is all the chip in and then raise
Validation | username in the login page shouldn’t contain special characters (like: $& *(@ ; - ) or space. Fix style of the page.
UI | fullscreen button
Security | timer in the server
UI | the player's sit, we dont need the name there
UI | blocks at top >>>> lobby doesn’t need the text and the first 3 blocks should wrap the content.
UI | slider should be presented only when it’s the players turn
UI | show the game rank at the end of the hand
UI | green to red color range timer, last 5 seconds need a sound
UX | notification , when a new player added or it’s the players turn
Security | get the ip address, location and mac address of a user
UI | sit in popup, a popup which asks the user to select the amoun of chips and confirm
01-04-2018
UI | SIT_OUT_ reduce the opacity of playerInfo div
UI | LOST >>>> text should be presented over the card, follow the style I put for the winner.

## Neil's Work
Job Done | Date done | Time Taken
Styling the old verticle slider | 24/03/2018 | 0:49
Improving the login page | 24/03/2018 | 1:04
styling the newer horizontal slider and setting the min and max | 25/03/2019 | 1:45
adding class "winner" and "loser" and styling at the end of game | 25/03/2020 | 1:35
| Total | 5:13
Experimental work done "Not actually used in project yet"
trying to "lock" screen to horizontal | 24/03/2018 | 1:30